## Sheet1
Week | What did we do yesterday? | What will we do today? | Any blockers?
Week 1 (Feb 15 – Feb 21) | Collected global renewable energy datasets (IEA/World Bank) | Clean and normalize country codes (ISO format) | Missing values in African countries
Week 1 (Feb 15 – Feb 21) | Finalized sprint scope and deliverables | Start exploratory data analysis (EDA) | None
Week 1 (Feb 15 – Feb 21) | Decided modeling direction: biofuel forecasting and classification | Import initial data into Colab | None
Week 2 (Feb 22 – Feb 28) | Region-wise country mapping (48 in Asia verified) | Implement classifier for continent-level grouping | Incomplete metadata for 3 countries
Week 2 (Feb 22 – Feb 28) | Created scripts for yearly trend visualization | Prepare seaborn/matplotlib plots | Data type mismatch in TIME column
Week 2 (Feb 22 – Feb 28) | Reviewed classification outputs | Plan forecasting module | None
Week 3 (Mar 1 – Mar 7) | Built time-series models (ARIMA, FB Prophet) | Test forecast for Asia + Europe | Model overfitting for Oceania
Week 3 (Mar 1 – Mar 7) | Validated country-level data inputs | Start plotting 2035 projections | TIME column not uniformly spaced
Week 3 (Mar 1 – Mar 7) | Designed reusable function for prediction | Deploy baseline graphs | None
Week 4 (Mar 8 – Mar 14) | Integrated investment trend datasets | Plot heatmaps: Investment vs Biofuel use | Merge inconsistencies
Week 4 (Mar 8 – Mar 14) | Evaluated correlation matrices | Drafted initial sprint retrospective | None
Week 4 (Mar 8 – Mar 14) | Region-wise visual review completed | Finalize forecasting outputs for presentation | High variance in South America data
Week 5 (Mar 15 – Mar 21) | Added country-wise forecast graphs | Validate completeness for all 48 Asian countries | Some entries like Japan missing initially
Week 5 (Mar 15 – Mar 21) | Started writing sprint summary | Build Eraser.io architecture diagram | Need feedback on system flow clarity
Week 5 (Mar 15 – Mar 21) | Ran QA checks on graphs | Archive all scripts and outputs | None
Week 6 (Mar 22 – Mar 28) | Final visual refinements | Export graphs to PDF/PNG | None
Week 6 (Mar 22 – Mar 28) | Wrote sprint retrospective | Start functional doc draft | Formatting issues
Week 6 (Mar 22 – Mar 28) | Checked model accuracy and MAPE | Generate prompts for architecture diagram | None
Week 7 (Mar 29 – Apr 4) | Finished Eraser.io prompt | Begin user stories and assumptions doc | None
Week 7 (Mar 29 – Apr 4) | Functional doc (goal, features, auth matrix) created | Review feedback and revise | Awaiting mentor input
Week 7 (Mar 29 – Apr 4) | Fine-tuned authorization matrix | Polish document for final submission | None
Week 8 (Apr 5 – Apr 15) | Reviewed everything: classification, forecasting, visuals | Submit final documents and code | None
Week 8 (Apr 5 – Apr 15) | Prepared sprint board and checklist | Backup code + notebooks to GitHub/Drive | None
Week 8 (Apr 5 – Apr 15) | Compiled and submitted final presentation deck | Ready sprint 2 planning if project extended | None